## Sheet1
Working Group | Neighbourhood Plan Steering Group
Note: Full details of the Sterring Groupp's acribioties can be found on the Oakham NPSG web site - oakhamnp.org.uk
Strategy | Action | By whom | Resources Reqd | Progress | Review Date | Completion Date
Lead and facilitate the production and maintenance of a Neighbourhood Plan | Steering Group membership details database | M Haley | none | Database populated | 8.1.16 | 9.1.16
| Meeting with Barleythorpe Meeting representatives 11.1.16 | A.Dewers M Haley | Council chamber | Meeting held | N/A | 11.1.16
| Steering Group meeting 14.1.16 | Steering Group | Council chamber | Draft Terms of Reference agreed. | 14.1.16 | 14.1.6
| Meeting with Barletythorpe Meeting representatives 21.1.16 | L Sanders F Payne M Haley | Council chamber | Meting held | N/A | 21.1.16
| Steering Group meeting 22.1.16 | Steering Group | none | Meeting held Draft Boundary submission agreed | N/A | 22.1.16
| Meeting with Egleton Meeting representatives 29.1.16 | L Sanders F Payne M Haley | Council chamber | Completed | N/A | 29.1.16
| Press and Radio contacts | L Sanders | none | On going
| Press release | L Sanders | none | Completed | N/A | 1.2.16
| Planning meeting 29.1.16 | L Sanders M Haley | Council chamber | Completed | N/A | 8.2.16
| Steering Group meeting 4.2.16 | Steering Group | Council chamber | Communications, Evidence Collation and Photographic WGs formed | N/A | !5.2.16
| Steering Group meeting 15.2.16 | Steering Group | Council chamber
| Communications WG meeting 29.2.16 | M Haley F Payne M Burns-Jones | Hire of VH Ballroom £100.00 Marketing materials £200.00 | Draft press release written. Date for first Public Engagement event agreed for 9 April. Quote to use VH ballroom received. | 16.3.16 | 16.3.16
| Steering Group meeting 29.2.16 | Steering Group |  | Working Group terms of reference. Events WG formed
| Evidence Working Group meeting 1.3.16 | M Hinmam M Haley | Wallet folders | Paper evidence documents to date filed
| Communications WG meeting 2.3.16 | M Haley F Payne M Burns-Jones | Council chamber | Draft press release 2 written | 2.3.16 | 2.3.16
| Communications WG meeting 9.3.16 | M Haley F Payne M Burns-Jones | Council chamber | Draft press release 3 written | 9.3.16 | 9.3.16
| Build web site | Steering Group | To be determined | Under construction | 16.3.16
| Photographic Working Group | M Brooks | USB drive( funded by Marketing materials) | Stock photos of Oakham produced and held on file | 1.3.16 | 14.3.16
| Communications WG meeting 15.2.16 | M Haley F Payne M Burns-Jones | Council chamber | Draft press release 4 written | 15.3.16 | 16.3.16
| Steering Group meeting 16.3.16 | Steering Group | Council Chamber | Town Centre working group formed. Plans for 9 April event formulated, agreed not to refer to NP boundary until after RCC announcement | 22.3.16
| Steering Group meeting 22.3.16 | Steering Group | Council chamber | Public engagement event for 9.4.16 arranged |  | 9.4.16
| Town centre Working Group meeting 22.3.16 | O Bird J Nowell M Haley | none | Arrangements for 9 April event agreed | N/A | 22.3.16
| Events Working Group to get quotation for leaflet printing, produce forms for public feedback | C Clark | agreed budget | Leaflets and feedback forms printed |  | 31.3.16
| Public engagement event 9.4.16 | Steering Group | Victoria Hall agreed budget | Event held | 15.4.16
| Steering Group meeting 15.4.16 | Steering Group | Council chamber | Public engagement event 9.4.16 feedback and analysis | 28.4.16 | 28.4.16
| Neighbourhood Plan web site | Steering Group | Set up and 2yr web domain name cost £96.00 Paper to be produced for OTC May Council meeting agenda | Paper submitted as an agenda item for May 2016 Council meeting | 11.5.16
| Meeting with RCC Planners | M Haley J Hopkins L Sanders | none | SLA established
| Neighbourhood Plan web site | Steering Group | agreed budget | Web site live and populated | on going | on going
| Steering Group meeting 27.6.16 | Steering Group | Council chamber | Working sub groups initiated outline plan until 3.17 agreed | 7.16
| Meeting with D Taylor, Chair of Stamford Town Council NP Steering Group | M Haley | Travel expenses to Stamford | Establish contact, discuss public engagement methods | 7.7.16 | 7.7.16
| Meeting with D Taylor, Chair of Stamford Town Council NP Steering Group | M Haley L Sanders | Travel expenses to Stamford | Discuss resident survey and working groups | 18.7.16 | on going
| Steering Group meeting 25.7.16 | Steering Group | Council chamber | Plan September mail drop View drawings produced by RCC Discuss grant application, Discuss SG training programme Prepare August press release | 7.16 | on going
| Neighbourhood Plan marketing material for mail drop to all properties within Oakham and Barleythorpe | M Haley | Art work and Printing costs £1500.00 | Letter, plans and leaflet proof prepared for printing. | 18..8.16
| Ditto | Assistant Clerk |  | Order raised for leaflet printing £375.00 | 25.8.16
| Steering Group meeting | Steering Group | Presentation by Chairman of Staford TC NPSG | none | 18.8.16 | 18.8.16
| Make contact with Tesco re hoisting engagement and information event | M Haley | none | on-line application in progress | 21.8.16 | 31.8.16
| Contact Farmers Market organiser re space for engagement and information event | J Hopkins | OTC gazebo
| Neighbourhood Plan event posters | M Haley | Printing costs £175.00 | Art work prepared for printing | 2016-09-01
| Tesco event arranged for 22 October 2016 | Steering Group | None | Completed | 6.9.16 | 2016-09-01
| Leaflet drop in Oakham and Barleythorpe | Steering Group | Council chamber | Completed | 2016-09-01 | 2016-09-01
| Neighbourhood Plan roller banners for engagement events | Steering Group | Production cost for 6 banners £384.00 +VAT | Completed | N/A | 2016-10-01
| Training programme developed | Steering Group | Council chamber | on going | 2016-11-01 | on going
| Training Session 1 delivered | Saunders Boston | Council chamber | Completed | N/A | 2016-10-01
| Arrange engagement event Farmers Market for 19.11.16 | Steering Group | OTC Gazebo | Completed |  | 2016-11-01
| Arrange survey production presentations | Steering Group | Council chamber | 3 Potential suppliers contacted, presentation dates arranged | 2016-11-01 | 2016-11-01
| Recommend survey consultant and associated costs | Steering Group | rcc@£4200.00 max. Printing costs £2300.00 | Order raised for rcc consultancy | 2017-03-01 | 2016-03-01
| Write paper for December OTC Council meeting requesting budget increase and agreement to proceed | M Haley | None | Completed | 2016-12-01 | 2016-12-01
| Prepare budget request for 2017/18 | M Haley | None | Completed | 2016-12-01 | 2016-12-01
| Hold awareness meeting with PROBUS, OTP and O/S Primary Schools at child collection times | Steering Group | Existing materials | Completed | 2016-12-01 | 2016-12-01
| Meet with consultants to agree survey format and questions | Steering Group | Council chamber | initial meeting held 12.12.16, WG meetings arranged for Jan-17 | 2017-02-01 | 2017-02-01
| Arrange Business Forum meeting | O.Bird, M Haley | V Hall | Arranged for 31.1.17 | 2017-02-01 | 2017-02-01
| Appoint J.Hopkins as Secretary to the SG in accordance with agreed Terms of Reference | Steering Group | None | Completed | N/A | 2016-12-01
| Request to increase budget for 2016/17 from £5000.00 to £6000.00 agreed by Council Dec 2016 meeting) | OTC | None | Completed | N/A | 2016-12-01
| Budget for 2017/18 set at £14000.00 | OTC | None | Completed | N/A | 2016-12-01
| Arrange and hold meeting with Business representatives | O.Bird | Victoria Hall | Completed | 2017-01-01 | 2017-01-01
| Meetings held between rcc and NPSGWGs to determine survey questions (draft) | Steering Group | Council Chamber | Completed | N/A | 2017-01-01
| Meetings held between rcc and SG to finalise survey questions | rcc, Steering Group | Council chamber | Completed | 2017-03-01 | 2017-02-01
| Arrange engagement events at Tesco and Aldi | Steering Group | Marketing materials | Completed | 2017-03-01 | 2017-03-01
| Agree final draft for survey printing and sponsorship | Steering Group | Council chamber | In progress | 2017-02-01 | 2017-03-01
| Contact sponsors | Steering Group | None | Completed | 2017-02-01 | 2017-03-01
| Produce and print event posters and handouts for engagement events | M Haley | ditto | Completed | 2017-02-01 | 2017-02-01
| Arrange survey delivery rota and collection points | Steering Group | None | Completed |  | 2017-03-01
| Raise order for survey questionnaire with Quoin | Office | TBA (circa £2300.00) | Completed | 2017-03-01 | 2017-03-01
| Raise order with rcc for envelope printing and pre-payment | Office | TBA |  | 2017-03-01 | 2017-03-01
| Distribute surveys and arrange drop of points | Steering Group | None | Completed | 2017-03-01 | 2017-04-01
| Raise order for Six web site annual renewal | Clerk | 75 |  | 2017-04-01
| Collect and upload paper surveys | Steering Group | None | Completed | 2017-04-01 | 2017-04-01
| Collate returns | rcc | Order raised March 17 | Completed | 2017-04-01 | 2017-05-01
| Publish returns on NPSG web | P Dowse | None | Completed | 2017-05-01 | 2017-07-01
| Arrange consultancy TOR (phase 2)/ send out invitations | P Dowse/ Clerk | Office services | Completed | 2017-06-01 | 2017-06-01
| Contact developers re engagement meetings and agree programme | A. Lewis | None |  | 2017-07-01
| SG restructure, amendment to Terms of Reference paper to June Council meeting | M Haley R Haynes | Council chamber | Completed | 2017-07-01 | 2017-06-01
| Chris Clark appointed Chairman, Cllr A Bennett elected as OTC representative | OTC | None | Completed | N/A | 2017-06-01
| Arrange public engagement event (survey results) 15 July 2017 | Steering Group | Victoria Hall | Completed | 2017-07-01 | 2017-07-01
| Prepare and submit press release 17 | M Haley | None | Completed | N/A | 2017-06-01
| Arrange developers engagement meetings | A Lewis | Council chamber | Completed | 2017-08-01 | 2017-07-01
| Engagement meeting arranged with Taylor Wimpey, St John sand St Ann Foundation, Larkfleet, Savill's/Merchant Adventurers. Marrons | A Lewis | Council chamber |  | 2017-09-01
| Attendance at NP Heritage course | A Lewis | 40 | Completed | N/A | 2017-07-01
| Appointment of N Taylor to SG | Steering Group | None | Completed | N/A | 2017-07-01
| Meeting with Barleythorpe PC representatives | M Haley C Clark | Council chamber | Completed | N/A | 2017-07-01
| Meeting with Cllr P Goodwin, Barleythorpe PC | M Haley C Clark | Council chamber | Completed | N/A | 2017-07-01
| Cllr P Goodwin and N.Taylor invited to join SG | Steering Group | None | Completed | N/A | 2017-08-01
| Engagement meeting with ST Johns and St Anns Foundation | Steering Group | Council chamber | Completed | N/A | 2017-08-01
| Engagement meeting with Taylor Wimpey | Steering Group | Council chamber | Completed | N/A | 2017-08-01
| Consultancy invitations review | Steering Group | Council chamber
| Engagement meeting with Larkfleet 7.9.17 | Steering Group | Council chamber | Completed | N/A | 2017-09-01
| Engagement meeting with Savilles 14.9.17 | Steering Group | Council chamber | Completed | N/A | 2017-09-01
| Paul Dadford invited to join S.G. | Steering Group | None |  | 2017-10-01
| Follow up consultancy quotes | C Clark | None |  | 2017-10-01
| Heritage assessment presentation | RCC Planning Officer | Council chamber | Completed | N/A | 2017-09-01
| Engagement meeting with Marrons 21.9.17 | Steering Group | Council chamber | Completed | N/A | 2017-09-01
| Press release regarding SG response to RCC Local Plan | M Haley M Burns-Jones | None | Completed | N/A | 2017-09-01
| Meeting with RCC Planning Officer | C Clark A Lewis | None | Completed | N/A | 2017-09-01
| Presentation by Open Plan Consultants Ltd | Steering Group | Council chamber | Completed | 2017-12-01 | 2017-11-01
| Locality expression of interest and funding bid for consultation support | Clerk's office | Office services | Completed | N/A | 2017-11-01
| Presentations by Open Plan and Sustainable Land Trust consultants | Steering Group | Council chamber | Completed | 2017-12-01 | 2017-12-01
| RCC invitation to comment on Town Centre redevelopment proposals | Steering Group | Council chamber |  | 2017-12-01 | 2017-12-01
| SG Chairman to present to November Council meeting | SG Chairman | None | Completed | 01/11/2017Dec-17 | 2017-11-01
| Resignation of Ann Lewis and Maureen Burns-Jones. OTC Chairman to send letters thanking for their contributions to the NPSG | M.Haley | Clerk's office | Completed | N/A | 2017-12-01
| Press release inviting potential members of SG | SG Chairman | None | Completed | 2017-12-01 | 2017-11-01
| Appointment of Deputy Chairman Paul Dowse elected | Steering Group | Council chamber | Completed | N/A | 2017-11-01
| 2 more developers have expressed an interest in presenting to the SG. S.G Chairman to ask for information before decideing | SG Chairman | None |  | 2017-12-01
| It was resolved that the survey analysis sent to RCC would form the SG's response to RCC's Town Centre consultation | Steering Group | None |  | N/A | 2017-12-01
| Resolved to recommend the apppointment of Iopen Plan's consultation submission | Steering Group | 11475
| Subject to resolution by Council to appoint Open Plan,( submission attached) apply for locality grant of £9,000.00 | Clerk's office